## Sheet1
Project Tracker |  |  | Percent over/under to highlight numbers | 25%
Project | Category | Assigned to | Estimated start | Estimated finish | Estimated duration (in days) | Actual Start | Actual finish | Actual Duration (in days) | Notes
Home Page | Website Development | Christopher Johnson | 2024-11-14 | 2024-11-23 | 9 | 2024-11-14 | 2024-11-17 | 3
About Page | Website Development | Crystal Chapman | 2024-11-14 | 2024-11-23 | 9 | 2024-11-17 | 2024-11-30 | 13
Shop Page - Specials | Website Development | Jaden Chapman | 2024-11-14 | 2024-11-23 | 9 | 2024-11-17 | 2024-11-30 | 13
Shop Page - Store | Website Development | Jaden Chapman | 2024-11-14 | 2024-11-23 | 9 | 2024-11-17 | 2024-12-01 | 14
Contact Page | Website Development | Kenneth Garrison | 2024-11-14 | 2024-11-23 | 9 | 2024-11-17 | 2024-11-24 | 7
Navbar | Website Development | Christopher Johnson | 2024-11-14 | 2024-11-23 | 9 | 2024-11-14 | 2024-11-20 | 6
Footer | Website Development | Christopher Johnson | 2024-11-14 | 2024-11-23 | 9 | 2024-11-14 | 2024-11-15 | 1
Storyboard | Report | Crystal Chapman | 2024-11-14 | 2024-11-20 | 6 | 2024-11-14 | 2024-11-16 | 2
FlowChart | Report | Christopher Johnson | 2024-11-14 | 2024-11-20 | 6 | 2024-11-14 | 2024-11-16 | 2
Package Completion | Report | Christopher Johnson | 2024-12-01 | 2024-12-03 | 2 | 2024-12-01 | 2024-12-04 | 3
Script | Presentation | Crystal Chapman | 2024-11-14 | 2024-11-23 | 9 | 2024-11-20 | 2024-11-30 | 10
Production | Presentation | Kenneth Garrison | 2024-11-23 | 2024-12-01 | 8 | 2024-12-01 | 2024-12-03 | 2
Page Description - About | Presentation | Crystal Chapman | 2024-11-23 | 2024-12-01 | 8 | 2024-12-02 | 2024-12-03 | 1
Page Description - Contact | Presentation | Kenneth Garrison | 2024-11-23 | 2024-12-01 | 8 | 2024-12-01 | 2024-12-02 | 1
Page Description - Store | Presentation | Jaden Chapman | 2024-11-23 | 2024-12-01 | 8 | 2024-12-02 | 2024-12-03 | 1
Page Description - Home | Presentation | Christopher Johnson | 2024-11-23 | 2024-12-01 | 8 | 2024-12-02 | 2024-12-03 | 1
WAVE/WebFX/PageSpeed | Testing | Kenneth Garrison | 2024-11-28 | 2024-12-03 | 5 | 2024-12-02 | 2024-12-03 | 1
Final Submission | Final Submission | Christopher Johnson | 2024-12-01 | 2024-12-04 | 3 | 2024-12-01 | 2024-12-04 | 3
Formulas:
Estimated duration (in days) = DAYS([Estimated finish],[Estimated start])
Actual Duration (in days) = DAYS([Actual finish],[Actual Start])