## Project tracker
Project tracker |  |  | Percent over/under to highlight numbers | 25% | [5 empty] | To update list options, select 'Setup'.
Project | Category | Assigned to | Estimated start | Estimated finish | Estimated duration (in days) | Actual start | Actual finish | Actual duration (in days) | Notes
Website Development | Home Page | Christopher Johnson | 2024-11-16 | 2024-11-23 | 7 | 2024-11-14
Website Development | About Page | Crystal Chapman | 2024-11-20 | 2024-11-23 | 3
Website Development | Shop Page - Specials | Jaden Chapman | 2024-11-20 | 2024-11-23 | 3
Website Development | Shop Page - Store | Jaden Chapman | 2024-11-20 | 2024-11-23 | 3
Website Development | Contact Page | Kenneth Garrison | 2024-11-20 | 2024-11-23 | 3
Website Development | Navbar | Christopher Johnson | 2024-11-20 | 2024-11-23 | 3
Report | Storyboard | Crystal Chapman | 2024-11-23 | 2024-12-01 | 8
Report | FlowChart | Jaden Chapman | 2024-11-23 | 2024-12-01 | 8
Report | Package Completion | Christopher Johnson | 2024-11-28 | 2024-12-01 | 3
Presentation | Script | Crystal Chapman | 2024-11-28 | 2024-12-01 | 3
Presentation | Production | Kenneth Garrison | 2024-11-28 | 2024-12-01 | 3
Final Submissions | Final Submission | Christopher Johnson | 2024-12-01 | 2024-12-04 | 3
SETUP

## Setup
| Setup |  | Project names, category names, and student names can all be modified. Additional rows can be added as needed by the team.
Project Name | Category Name | Student Name
Report | Home Page | Christopher Johnson
Website Development | About Page | Crystal Chapman
Presentation | Shop Page - Specials | Jaden Chapman
| Shop Page - Store | Kenneth Garrison
Contact Page
Navbar
Storyboard
FlowChart
Package Completion
Script
Production
Final Submission
PROJECTS